## TASK TRACKER
S/N | PHASE | TEAM | COMPONENT | TASK | RESPONSIBLE | STATUS | START DATE | END DATE
1 | PHASE 1 | TEAM 1 | Consumer Module | Read XML files convert to JSON and Persist in MongoDB
2 |  | TEAM 1 | Consumer Module | Implement Consumer Settings No of threads
3 |  | TEAM 1 | Consumer Module | Implement Consumer Setting Consume specific files
4 |  | TEAM 1 | Consumer Module | Implement Consumer Setting Start and Stop
5 | PHASE 1 | TEAM 1 | Validator Module | Basic Form Validations Pharmacy Form
6 | PHASE 1 | TEAM 1 | Validator Module | Basic Form Validations ART Commencement
7 | PHASE 1 | TEAM 1 | Validator Module | Basic Form Validation Lab Forms
8 | PHASE 1 | TEAM 1 | Validator Module | Basic Form Validation HIV Enrollment Forms
9 | PHASE 1 | TEAM 1 | Validator Module | Basic Form Validation Care Card
10 | PHASE 1 | TEAM 1 | Validator Module | Store Validation Errors in the database
11 | PHASE 1 | TEAM 1 | ETL | Read JSON documents from Mongodb and create ART Line List
12 | PHASE 1 | TEAM 1 | ETL | Read JSON documents from Mongodb and create HTS Line List
13 |  | TEAM 1 | ETL | Read JSON documents from Mongodb and create PMTCT Line List
14 |  | TEAM 1 | ETL | Read JSON documents from Mongodb and create Biometric Line List
15 |  | TEAM 1 | Cohort Module | Cohort Build all Fundamental Cohorts
16 |  | TEAM 1 | Cohort Module | Cohort Build all Derived Cohort TX_CURR and disagregations
17 |  | TEAM 1 | Cohort Module | Cohort Build all Derived Cohort TX_NEW and disagregations
18 |  | TEAM 1 | Cohort Module | Cohort Build all Derived Cohort TX_PVLS and disagregations
19 |  | TEAM 1 | Cohort Module | Cohort Build all Derived Cohort TX_ML and disagregations
20 |  | TEAM 1 | Cohort Module | Cohort Build all Derived Cohort TX_RTT and disagregations
21 |  | TEAM 1 | Deduplication Module | Match fingerprint template and create a deduplication report
22 |  | TEAM 1 | NDR Generation Module | Generate NDR XMLs for sites with concurrence issues or for entire sites
23 |  | TEAM 1 | Data Triangulation Module | Triangulate line list data NDR vs CDR
24 |  | TEAM 1 | Data Triangulation Module | Triangulate line list data CDR vs EMR
25 |  | TEAM 1 | Data Triangulation Module | Triangulate aggregate data CDR vs NDR
26 |  | TEAM 1 | Data Triangulation Module | Triangualte aggregate data CDR vs DHIS
27 |  | TEAM 1 | Data Triangulation Module | Triangualte aggregate data CDR vs DATIM
28 | PHASE 1 | TEAM 1 | Data Quality Module | Data Quality Dashboards and Line List
29 | PHASE 1 | TEAM 1 | Reporting Module | ART Line List Export (Fixed Periods)
30 |  | TEAM 1 | Reporting Module | PMTCT Line List Export (Fixed Periods)
31 | PHASE 1 | TEAM 1 | Reporting Module | HTS Line List Export (Fixed Periods)
32 | PHASE 1 | TEAM 1 | Reporting Module | Biometric Line List Export
33 |  | TEAM 1 | Reporting Module | Missed Appointment Line List Export
34 |  | TEAM 1 | Reporting Module | Viral Load Eligible Line List Export
|  | TEAM 1 | Web API | API layer over the CDR
35 |  | TEAM 2 | UI/UX | Upload accept XML zip files
36 |  | TEAM 2 | UI/UX | Prevent clients from changing the name of zip files
37 |  | TEAM 2 | UI/UX | Store zip files in staging folder
38 |  | TEAM 2 | UI/UX | UI Design
39 |  | TEAM 1 | Analytics and Dashboards | CQI Dashboards
40 |  | TEAM 1 | Analytics and Dashboards | CBS Dashboards
41 |  | TEAM 1 | Analytics and Dashboards | Performance Dashboards
42 |  | TEAM 1 | Analytics and Dashboards | Mortality Dashboards
43 |  | TEAM 1 | Analytics and Dashboards | HTS Dashboards
44 |  | TEAM 1 | Analytics and Dashboards | Retention Dashabords
45 |  | TEAM 1 | Analytics and Dashboards | Viral Load Monitoring Dashboards
46 |  | TEAM 1 | NMRS Synch Module | Create Synch module on NMRS to exchange data over the web with Consumer services
47 |  | TEAM 1 | Consumer Module | Update Consumer to accept JSON data direct from the synch module
48 | PHASE 1 | TEAM 2 | Dataset Definition | Define Variables for ART Line List
49 | PHASE 1 | TEAM 2 | Dataset Definition | Define Variables for PMTCT Line List
50 | PHASE 1 | TEAM 2 | Dataset Definition | Define Variables for HTS Line List
51 | PHASE 1 | TEAM 2 | Dataset Definition | Define Variables for Biometric Line List
52 | PHASE 1 | TEAM 2 | Cohort Definition | Indicators for ART Line List
53 |  | TEAM 2 | Cohort Definition | Indicators for PMTCT Line List
54 |  | TEAM 2 | Cohort Definition | Indicators for HTS Line List
55 |  | TEAM 2 | Cohort Definition | Indicators for Biometric Line List
56 |  | TEAM 2 | Other Cohort Definitions | Custom Indicators
57 |  | TEAM 2 | Dashboard Templates | Dashboard Templates for CBS Surveilance
58 | PHASE 1 | TEAM 2 | Dashboard Templates | Dashboard Templates for Viral Load Monitoring
59 | PHASE 1 | TEAM 2 | Dashboard Templates | Dashboard Templates for Retention
60 | PHASE 1 | TEAM 2 | Dashboard Templates | Dashboard Templates for Performance Monitoring
61 |  | TEAM 2 | Dashboard Templates | Dashboard Templates for CQI
62 |  | TEAM 2 | Dashboard Templates | Dashboard Templates for ART Optimization
63 |  | TEAM 2 | Dashboard Templates | Dashboard Tempates for Data Quality
64 | PHASE 1 | TEAM 2 | Validation Rules | Validation Rule for Care Card
65 | PHASE 1 | TEAM 2 | Validation Rules | Validation Rule for Pharmacy
66 | PHASE 1 | TEAM 2 | Validation Rules | Validation Rules for ART Commencement
67 | PHASE 1 | TEAM 2 | Validation Rules | Validation Rules for HIV Enrollment
68 | PHASE 1 | TEAM 2 | Validation Rules | Validation Rules for Lab Form
69 |  | TEAM 3 | DevOps/Testing | Testing of Consumer use case XML consumption (30,000)
70 |  | TEAM 3 | DevOps/Testing | Testing of Consumer use case setting of threads
71 |  | TEAM 3 | DevOps/Testing | Tesing of Consumer setting consume specific files
72 |  | TEAM 3 | DevOps/Testing | Testing of Consumer setting start and stop
73 |  | TEAM 3 | DevOps/Testing | Testing of Validator use cases
74 |  | TEAM 3 | DevOps/Testing | Testing of ETL use cases
75 | PHASE 1 | TEAM 3 | Project Management | Documentation of architectural diagrams
76 | PHASE 1 | TEAM 3 | Project Management | Documentation of database diagrams
77 | PHASE 1 | TEAM 3 | Project Management | Maintain Project Management Tracker
78 | PHASE 1 | TEAM 3 | Project Management | Organize routine follow up meetings
79 |  | TEAM 3 | Project Management | Create new tasks
80 |  | TEAM 3 | Project Management | Create knowledge repository on Confluence
81 | PHASE 1 | TEAM 3 | Project Management | Research and Development
82 | PHASE 1 | TEAM 3 | Project Management | Governance and Accountability Framework

## CODES
TEAM
TEAM 1
TEAM 2
TEAM 3